## Sheet1
BI-WEEKLY REPORT - ACTIVE WORK SITES
NO. | DIVISION/GROUP | STREET NO. | STREET NAME | BASIN/WATERSHED | COUNCIL DISTRICT | Work Type (Sewer/Water/Storm) | Responsible Party (DWM Crew or Contractor's Name) | Last Date of Communication to Residents | Last Date of Communication to Council Member | STATUS | START DATE | PROJECTED COMPLETION DATE
1 | CWA | 2842 | CRESCENDO DR | SDC03 | 10 | SEWER | RPL/IMS | 2019-11-01 |  | PENDING | 2019-11-04 | 2019-11-15
2 | CWA | 3034 | BAKER RIDGE DR | SDC03 | 10 | SEWER | RPL/IMS | 2019-11-01 |  | PENDING | 2019-11-04 | 2019-11-15
3 | CWA | 3942 | BAKER FERRY RD | SDC01A | 10 | SEWER | RPL/IMS | 2019-10-14 |  | PENDING | 2019-11-04 | 2019-11-15
4 | CWA | 1069 | OLLIE STREET | PRC05B | 3 | SEWER | RPL/IMS | 2019-10-01 |  | PENDING | 2019-11-04 | 2019-11-18
5 | CWA | 2456 | MLK JR DR NW | SDC03B1 | 10 | SEWER | RPL/IMS | 2019-10-01 |  | PENDING | 2019-11-05 | 2019-11-08
6 | CWA | 920 | RICE STREET | PRC05C | 3 | SEWER | RPL/IMS | 2019-10-29 |  | PENDING | 2019-11-06 | 2019-11-15
7 | CWA | 1281 | FAIR STREET | PRC15A | 4 | SEWER | RPL/IMS | 2019-10-29 | 2019-10-28 | PENDING | 2019-11-05 | 2019-11-15
8 | CWA | 892 | JEFFERSON STREET | PRC05C1 | 3 | SEWER | RPL/IMS | 2019-10-14 |  | PENDING | 2019-11-01 | 2019-11-15
9 | CWA | 1314 | DONALD LEE HWY | PRC05B | 3 | SEWER | RPL/IMS | 2019-10-01 |  | PENDING | 2019-11-05 | 2019-11-15
10 | CWA | 918 | MARIETTA BLVD | PRC05C | 3 | SEWER | RPL/IMS | 2019-10-19 |  | PENDING | 2019-11-05 | 2019-11-15
11 | CWA | 2655 | DONALD LEE HWY | PRC05B | 3 | SEWER | RPL/IMS | 2019-10-14 |  | PENDING | 2019-11-05 | 2019-11-18
12 | CWA | 2641 | DONALD LEE HWY | PRC05B | 3 | SEWER | RPL/IMS | 2019-10-01 |  | PENDING | 2019-11-05 | 2019-11-15
13 | CWA | 1922 | MAIN STREET NW | PTC-PRC02 | 9 | SEWER | RPL/IMS | 2019-10-15 |  | PENDING | 2019-11-05 | 2019-11-15
14 | CWA | 184 | SCOTT STREET | PRC05B | 3 | SEWER | RPL/IMS | 2019-09-01 |  | PENDING | 2019-11-04 | 2019-11-15
15 | CWA | 1005 | WASHINGTON HEIGHT | PRC05B | 3 | SEWER | RPL/IMS | 2019-09-01 |  | PENDING | 2019-11-04 | 2019-11-15
16 | CWA | 1014 | WASHINGTON HEIGHT | PRC05B | 3 | SEWER | RPL/IMS | 2019-09-01 |  | PENDING | 2019-11-05 | 2019-11-15
17 | CWA | 1017 | WASHINGTON HEIGHT | PRC05B | 3 | SEWER | RPL/IMS | 2019-09-01 |  | PENDING | 2019-11-05 | 2019-11-15
18 | CWA | 1037 | WASHINGTON HEIGHT | PRC05B | 3 | SEWER | RPL/IMS | 2019-09-01 |  | PENDING | 2019-11-05 | 2019-11-15
19 | CWA | 1034 | WASHINGTON HEIGHT | PRC05B | 3 | SEWER | RPL/IMS | 2019-09-01 |  | PENDING | 2019-11-05 | 2019-11-15
20 | CWA | 1358 | EASON STREET | PRC15 | 3 | SEWER | RPL/IMS | 2019-08-29 |  | PENDING | 2019-11-07 | 2019-11-15
21 | CWA | 673 | RICE STREET | PRC05B | 3 | SEWER | RPL/IMS | 2019-08-15 |  | PENDING | 2019-11-05 | 2019-11-15
22 | CWA | 949 | W MARIETTA ST NW | PRC05C | 3 | SEWER | RPL/IMS | 2019-07-29 |  | PENDING | 2019-11-12 | 2019-11-15
23 | CWA | 1175 | HIGHTOWER RD | PRC13 | 9 | SEWER | RPL/IMS | 2019-07-30 |  | PENDING | 2019-11-12 | 2019-11-15
24 | CWA | 941 | RIDGE AVE NW | PRC13A1 | 9 | SEWER | RPL/IMS | 2019-08-05 |  | PENDING | 2019-11-04 | 2019-11-15
25 | CWA | 2591 | COLLIER DR NW | SDC03B | 10 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-05 | 2019-11-15
26 | CWA | 2819 | COLLIER DR NW | SDC03B | 10 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-08 | 2019-11-15
27 | CWA | 25 | CHAPPELL RD (CSX RAILROAD) | PRC15 | 3 | SEWER | RPL/IMS | 2019-10-30 |  | PENDING | 2019-11-06 | 2019-11-15
28 | CWA | 2457 | MLK JR DR/HAMILTON E HOLMES | SDC03B1 | 10 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-07 | 2019-11-14
29 | CWA | 3746 | Parian Ridge Rd NW | LICB | 8 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-04 | 2019-11-15
30 | CWA | 1018 | Niles Ave NW | PRC05C | 3 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-04 | 2019-11-15
31 | CWA | 965 | Baylor St NW | PRC05C | 3 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-04 | 2019-11-15
32 | CWA | 949 | Longley Ave NW | PRC05C | 3 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-04 | 2019-11-15
33 | CWA | 950 | Longley Ave NW | PRC05C | 3 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-04 | 2019-11-15
34 | CWA | 1075 | 5th St NW | PRC13 | 9 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-04 | 2019-11-15
35 | CWA | 859 | Ridge Ave NW | PRC13A1 | 9 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-04 | 2019-11-15
36 | CWA | 1191 | Wedgewood Dr NW | PRC13BZ | 9 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-04 | 2019-11-15
37 | CWA | 2776 | Mango Cl NW | PRC13BZ | 9 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-04 | 2019-11-15
38 | CWA | 11 | Chappell Road | PRC15 | 3 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-04 | 2019-11-15
39 | CWA | 1284 | Akridge St NW | PRC15 | 3 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-04 | 2019-11-15
40 | CWA | 36 | Burbank Dr NW | PRC15 | 3 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-04 | 2019-11-15
41 | CWA | 58 | Rockmart Outfall | PRC15 | 3 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-04 | 2019-11-15
42 | CWA | 1338 | Thurgood St SW | PRC15A | 3 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-04 | 2019-11-15
43 | CWA | 251 | Hopkins St SW | PRC15A | 3 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-04 | 2019-11-15
44 | CWA |  | Bolton Rd NW | PRC17_18B | 9 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-04 | 2019-11-15
45 | CWA | 1286 | Northwest Dr NW | PRC17_18B | 9 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-04 | 2019-11-15
46 | CWA |  | Watkins St NW Outfall | PRC17_18B | 9 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-04 | 2019-11-15
47 | CWA | 2127 | Bolton Rd SW | PTC-PRC02 | 9 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-04 | 2019-11-15
48 | CWA | 2128 | Bolton Rd SW | PTC-PRC02 | 9 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-04 | 2019-11-15
49 | CWA | 2209 | Bolton Rd NW | PTC-PRC02 | 9 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-04 | 2019-11-15
50 | CWA | 2414 | Claude St NW | PTC-PRC02 | 9 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-04 | 2019-11-15
51 | CWA | 2107 | Claude St NW | PTC-PRC02 | 9 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-04 | 2019-11-15
52 | CWA | 2090 | Claude St NW | PTC-PRC02 | 9 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-04 | 2019-11-15
53 | CWA |  | Marietta Rd NW | PTC-PRC02 | 9 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-04 | 2019-11-15
54 | CWA | 28 | Candlelight Ln SW | SDC01A | 10 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-04 | 2019-11-15
55 | CWA | 4061 | Kenora Dr SW | SDC01A | 10 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-04 | 2019-11-15
56 | CWA | 3977 | Ferry Heights Dr SW | SDC01A | 10 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-04 | 2019-11-15
57 | CWA | 3791/3940 | Rutgers Dr SW | SDC01A | 10 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-04 | 2019-11-15
58 | CWA | 3791/3987 | Adamsville Dr SW | SDC01A | 10 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-04 | 2019-11-15
59 | CWA | 3790/3990 | Adamsville Dr SW | SDC01A | 10 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-04 | 2019-11-15
60 | CWA | 3790/3990 | Adamsville Dr SW | SDC01A | 10 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-04 | 2019-11-15
61 | CWA | 514 | Larchmont Cl NW | SDC03 | 10 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-04 | 2019-11-15
62 | CWA | 3043 | Caron Cl NW | SDC03 | 10 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-04 | 2019-11-15
63 | CWA | 755 | Caron Cl NW | SDC03 | 10 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-04 | 2019-11-15
64 | CWA | 619 | Skipper Drive NW | SDC03 | 10 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-04 | 2019-11-15
65 | CWA |  | Larchmont Cl NW Outfall | SDC03 | 10 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-04 | 2019-11-15
66 | CWA |  | Larchmont Cl NW Outfall | SDC03 | 10 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-04 | 2019-11-15
67 | CWA | 381 | Waterford Rd NW | SDC03B | 10 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-04 | 2019-11-15
68 | CWA | 2633 | Hightower Ct NW | SDC03B | 10 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-04 | 2019-11-15
69 | CWA | 2633 | Hightower Ct NW | SDC03B | 10 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-04 | 2019-11-15
70 | CWA | 2640 | Hightower Ct NW | SDC03B | 10 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-04 | 2019-11-15
71 | CWA | 274 | Simon Te NW | SDC03B | 10 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-04 | 2019-11-15
72 | CWA | 787 | Duffield Dr NW | SDC03B | 10 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-04 | 2019-11-15
73 | CWA | 97 | Hollis Te NW | SDC03B1 | 10 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-04 | 2019-11-15
74 | CWA | 97 | Hollis Te NW | SDC03B1 | 10 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-04 | 2019-11-15
75 | CWA | 2777 | Hedgewood Ln NW | SDC03B1 | 10 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-04 | 2019-11-15
76 | CWA | 2801 | Valley Heart Dr NW | SDC03B1 | 10 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-04 | 2019-11-15
77 | CWA | 2811 | Valley Heart Dr NW | SDC03B1 | 10 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-04 | 2019-11-15
78 | CWA | 2685 | DONALD LEE HWY | PRC13A1 | 9 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-04 | 2019-11-15
79 | CWA | 1941 | FELKER WARD STREET | PTC-PRC02 | 9 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-04 | 2019-11-15
80 | CWA | 2352 | BOLTON RD | PTC-PRC02 | 9 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-04 | 2019-11-15
81 | CWA | 2100 | SPINK STREET | PTC-PRC02 | 9 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-04 | 2019-11-15
82 | CWA | 3920 | PARION RIDGE ROAD | LICB | 8 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-04 | 2019-11-15
83 | CWA | 1352 | ANDREW STREET | PRC05B | 3 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-04 | 2019-11-15
84 | CWA | 1061 | W MARIETTA ST NW | PRC05C | 3 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-04 | 2019-11-15
85 | CWA | 2640 | WHITING STREET | PRC13A1 | 9 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-04 | 2019-11-15
86 | CWA | 841 | RIDGE AVE NW | PRC13A1 | 9 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-04 | 2019-11-15
87 | CWA | 1202 | Wedgewood Dr NW (OUTFALL) | PRC13BZ | 9 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-04 | 2019-11-15
88 | CWA | 1188 | Wedgewood Dr NW (OUTFALL) | PRC13BZ | 9 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-04 | 2019-11-15
89 | CWA | 1436 | SHARON STREET | PRC15 | 3 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-04 | 2019-11-15
90 | CWA | 1358 | SCOTT STREET | PRC15 | 3 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-04 | 2019-11-15
91 | CWA | 64 | Rockmart Outfall | PRC15 | 3 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-04 | 2019-11-15
92 | CWA |  | CHAPPELL AND BERNARD | PRC15 | 3 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-04 | 2019-11-15
93 | CWA | 54 | CHAPPELL | PRC15 | 3 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-04 | 2019-11-15
94 | CWA | 1344 | EASON STREET | PRC15 | 3 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-04 | 2019-11-15
95 | CWA | 176 | STANHOPE CIRCLE | PRC15 | 3 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-04 | 2019-11-15
96 | CWA | 9 | Burbank Dr NW | PRC15 | 3 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-04 | 2019-11-15
97 | CWA | 1720 | MLK JR DR NW | PRC15A | 3 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-04 | 2019-11-15
98 | CWA | 122 | Burbank Dr NW | PRC15A | 3 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-04 | 2019-11-15
99 | CWA | 1225 | WESTVIEW DRIVE | PRC15A | 3 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-04 | 2019-11-15
100 | CWA | 1201 | WESTVIEW DRIVE | PRC15A | 3 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-04 | 2019-11-15
101 | CWA | 1400 | NORTHWEST DRIVE | PRC17-18B | 9 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-04 | 2019-11-15
102 | CWA | 1926 | MAIN STREET NW | PTC-PRC02 | 9 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-05 | 2019-11-15
103 | CWA | 2360 | BOLTON RD | PTC-PRC02 | 9 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-05 | 2019-11-15
104 | CWA | 3942 | BAKER FERRY RD | SDC01A | 10 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-05 | 2019-11-15
105 | CWA | 2936 | BAKER RIDGE DR | SDC03B | 10 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-05 | 2019-11-15
106 | CWA | 2544 | DALE CREEK | SDC03B | 10 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-05 | 2019-11-15
107 | CWA | 2499 | DALE CREEK | SDC03B | 10 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-05 | 2019-11-15
108 | CWA | 2511 | DALE CREEK | SDC03B | 10 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-05 | 2019-11-15
109 | CWA | 2596 | DALE CREEK | SDC03B | 10 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-05 | 2019-11-15
110 | CWA | 2535 | SANTA BARBARA | SDC03B | 10 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-05 | 2019-11-15
111 | CWA | 2716 | COLLIER DR NW | SDC03B | 10 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-05 | 2019-11-15
112 | CWA | 819 | DUFFIELD STREET | SDC03B | 10 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-05 | 2019-11-15
113 | CWA | 436 | FORREST RIDGE | SDC03B | 10 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-05 | 2019-11-15
114 | CWA |  | H.E.HOLMES MARTA STATION | SDC03B1 | 10 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-05 | 2019-11-15
115 | CWA | 2670 | LOGHAVEN DRIVE | SDC03B1 | 10 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-05 | 2019-11-15
116 | CWA | 2542 | LOGHAVEN DRIVE | SDC03B1 | 10 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-05 | 2019-11-15
117 | CWA | 2542 | GODFREY DRIVE | SDC03B1 | 10 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-05 | 2019-11-15
118 | CWA | 2622 | GODFREY DRIVE | SDC03B1 | 10 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-05 | 2019-11-15
119 | CWA | 2875 | Valley Heart Dr NW | SDC03B1 | 10 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-05 | 2019-11-15
120 | CWA | 38 | HAMILTON E. HOLMES | SDC03B1 | 10 | SEWER | RPL/IMS |  |  | PENDING | 2019-11-04 | 2019-11-15
121
122