## Sheet1
BI-WEEKLY REPORT - ACTIVE WORK SITES
NO. | DIVISION/GROUP | STREET NO. | STREET NAME | BASIN/WATERSHED | COUNCIL DISTRICT | Work Type (Sewer/Water/Storm) | Responsible Party (DWM Crew or Contractor's Name) | Last Date of Communication to Residents | Last Date of Communication to Council Member | STATUS | START DATE | PROJECTED COMPLETION DATE
1 | OLIO |  | Wieuca Rd NE ( from GA 400 to Phipps Blvd) | Nancy Creek | 7 | Water | Reeves Young | 2019-11-01 | 2019-11-01 | Active | 2019-06-03 | 2019-11-21
2 | OLIO |  | Nelson street ( from Haynes St to Mangum St) | Proctor Creek | 3 | Water | Reeves Young Sub ( Anderson Grading & Pipeline) | 2019-10-28 | 2019-10-02 | Active | 2019-08-24 | 2019-11-15
3 | OLIO |  | William Holmes Borders Senior Drive and Edgewood Ave | Peachtree Creek | 5 | Water | Reeves Young Sub ( Anderson Grading & Pipeline) | 2019-08-09 | 2019-08-09 | Active | 2019-11-06 | 2020-11-21
4 | OLIO | 651 | 14 Street | Proctor Creek | 3 | Water | Reeves Young | N/A | N/A | Active | 2019-03-14 | 2020-01-21
5 | OLIO | 689 | Connally Rd | Intrenchment Creek | 1 | Water | Reeves Young | Not Yet | Not Yet | Active | 2019-11-11 | 2020-11-21
6 | OLIO | 2911 | Metropolitan Pkwy | South River | 12 | Water | Reeves Young sub ( Titan Unlimited) | Not Yet |  | Active | 2019-11-11 | 2020-11-21
7 | OLIO | 2180 | Ohara Pl SE | South River | 1 | Water | Reeves Young sub ( Titan Unlimited) | Not Yet |  | Active | 2019-11-11 | 2020-11-21
8 | OLIO | 45 | Forsyth St. SW | Proctor Creek | 4 | Water | Reeves Young sub ( Titan Unlimited) | Not Yet |  | Active | 2019-11-11 | 2020-11-21
9 | OLIO | 565 | Wells St. SW | South River | 4 | Water | Reeves Young sub ( Titan Unlimited) | Not Yet |  | Active | 2019-11-11 | 2020-11-21
10 | OLIO | 2211 | Bent Creek Way SW | Utoy Creek | 11 | Water | Reeves Young sub ( Titan Unlimited) | Not Yet |  | Active | 2019-11-11 | 2020-11-21
11 | OLIO | 2869 | Parrott Ave NW | Proctor Creek | 9 | Water | Reeves Young sub ( Titan Unlimited) | Not Yet |  | Active | 2019-11-11 | 2020-11-21
12 | OLIO | 285 | Ralph D. Abernathy Blvd SW | Intrenchment Creek | 4 | Water | Reeves Young sub ( Titan Unlimited) | Not Yet |  | Active | 2019-11-11 | 2020-11-21
13 | OLIO | 1787 | Brewer Blvd SW | South River | 12 | Water | Reeves Young sub ( Titan Unlimited) | Not Yet |  | Active | 2019-11-11 | 2020-11-21
14 | OLIO | 371 | Paces Ferry Rd NW | Nancy Creek | 8 | Water | Reeves Young sub ( Titan Unlimited) | Not Yet |  | Active | 2019-11-11 | 2020-11-21
15 | OLIO | 3039 | 1st Ave | South River | 12 | Water | Reeves Young sub ( Titan Unlimited) | Not Yet |  | Active | 2019-11-11 | 2020-11-21
16 | OLIO | 2419 | Meadow Park Dr SW | South River | 12 | Water | Reeves Young sub ( Titan Unlimited) | Not Yet |  | Active | 2019-11-11 | 2020-11-21
17 | OLIO | 1075 | Peachtree St NE | Peachtree Creek | 2 | Water | Reeves Young sub ( Titan Unlimited) | Not Yet |  | Active | 2019-11-11 | 2020-11-21
18 | OLIO | 3100 | Parrott Ave NW | Proctor Creek | 9 | Water | Reeves Young sub ( Titan Unlimited) | Not Yet |  | Active | 2019-11-11 | 2020-11-21
19 | OLIO | 745 | Collier Rd NW | Peachtree Creek | 8 | Water | Reeves Young sub ( Titan Unlimited) | Not Yet |  | Active | 2019-11-11 | 2020-11-21
20 | OLIO | 575 | Junipe St. NE | Peachtree Creek | 2 | Water | Reeves Young sub ( Titan Unlimited) | Not Yet |  | Active | 2019-11-11 | 2020-11-21
21 | OLIO | 500 | Fairburn Rd | Sandy Creek | 10 | Water | Rockdale Pipeline | Not Yet |  | Active | 2019-11-11 | 2020-11-21
22 | OLIO |  | Northside Dr. and Mooresmill Rd NW | Nancy Creek | 8 | Water | Rockdale Pipeline | Not Yet |  | Active | 2019-10-04 | 2020-12-20
23 | OLIO | 192 | Jessie Hill Jr. Dr. SE | Peachtree Creek | 5 | Water | Rockdale Pipeline | Not Yet |  | Active | 2019-10-21 | TBD
24 | OLIO | 447 | Flatshoals Ave. SE | Intrenchment Creek | 5 | Water | Rockdale Pipeline | Not Yet |  | Active | 2019-11-11 | 2020-11-21
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50