## Sheet1
BI-WEEKLY REPORT - ACTIVE WORK SITES
NO. | DIVISION/GROUP | STREET NO. | STREET NAME | BASIN/WATERSHED | COUNCIL DISTRICT | Work Type (Sewer/Water/Storm) | Responsible Party (DWM Crew or Contractor's Name) | Last Date of Communication to Residents | Last Date of Communication to Council Member | STATUS | START DATE | PROJECTED COMPLETION DATE
1 | OES | 3905 | Wieuca RD NE | Nancy Creek | 7 | Storm | SESD/LCS | 2019-10-11 | 2019-10-31 | Construction | 2019-08-06 | 2019-11-08
2 | OES | 1756 & 1631 | W Paces Ferry Rd | Nancy Creek | 8 | Storm | SESD/LCS | 2019-09-18 | 2019-09-18 | Construction | 2019-08-05 | 2019-11-08
3 | OES | 956 | Washington Pl | Proctor Creek | 4 | Storm | SESD/LCS | 2019-10-12 | 2019-10-10 | Construction | 2019-10-08 | 2020-02-04
4 | OES | 973 | Mercer Street | Intrenchment Creek | 1 | Storm | Kemi | 2019-09-19 | 2019-09-26 | Construction | 2019-10-21 | 2019-12-20
5 | OES |  | Peachtree Hills Ave NE | Peachtree Creek | 7 | Storm | Kemi | 2019-10-16 | 2019-10-10 | Construction | 2019-10-14 | 2019-12-20
6 | OES |  | Ralph David Abernathy Boulevard Segm 2 | Intrenchment Creek | 4 | Storm | Kemi |  |  | Proposal Submission | 2019-11-18 | 2020-01-17
7 | OES |  | Dean Rusk Park | Proctor Creek | 4 | Storm | SESD/LCS |  |  | Proposal Submission | 2020-01-01 | 2020-07-01
8 | OES | 740 | Wesley Drive | Peachtree Creek | 8 | Storm | Kemi |  |  | Proposal Submission | 2019-12-01 | 2020-03-20
9 | OES | 800 | Hutchens Rd | South River | 12 | Storm |  |  |  | Design | 2019-11-20 | 2019-12-20
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50