## Contract D 11-01-2019
BI-WEEKLY REPORT - ACTIVE WORK SITES
NO. | DIVISION/GROUP | STREET NO. | STREET NAME | BASIN/WATERSHED | COUNCIL DISTRICT | Work Type (Sewer/Water/Storm) | Responsible Party (DWM Crew or Contractor's Name) | Last Date of Communication to Residents | Last Date of Communication to Council Member | STATUS | START DATE | PROJECTED COMPLETION DATE
1 | CWA | 2337 | 1st Avenue NE | SGC03 | 5 | Sewer | Granite/TJ | 2019-10-25 |  | Active | 2019-10-28 | 2019-11-01
2 | CWA | 139 | East Lake Terrace SE | SGC04A | 5 | Sewer | Granite/TJ | 2019-10-24 | 2019-10-25 | Active | 2019-10-28 | 2019-11-01
3 | CWA | 2727 | Hosea L Williams Drive NE | SGC04A | 5 | Sewer | Granite/TJ | 2019-10-23 |  | Active | 2019-10-29 | 2019-11-04
4 | CWA | 2529 | Hosea L Williams Drive SE | SGC04A | 5 | Sewer | Granite/TJ | 2019-10-27 |  | Active | 2019-10-30 | 2019-11-05
5 | CWA | 2425 | Hosea L Williams Drive NE | SGC04A | 5 | Sewer | Granite/TJ | 2019-10-27 |  | Active | 2019-10-30 | 2019-11-05
6 | CWA | 155-175 | East Lake DrSE | SGC04A | 5 | Sewer | Granite/TJ | 2019-10-10 | 2019-10-15 | Active | 2019-10-30 | 2019-11-05
7 | CWA | 27 | Rocky Ford SE | SGC03 | 5 | Sewer | Granite/TJ | 2019-10-28 |  | Active | 2019-10-31 | 2019-11-06
8 | CWA | 2727 | Hosea Williams Drive NE | Sgcova | 1 | Sewer | Granite/TJ | 2019-10-29 |  | Pending | 2019-11-04 | 2019-11-05
9 | CWA | 34 | East Lake Drive NE | SGC03 | 5 | Sewer | Granite/TJ | 2019-11-01 |  | Pending | 2019-11-04 | 2019-11-08
10 | CWA | 34-58 | East Lake Drive NE | SGC04A | 5 | Sewer | Granite/TJ | 2019-11-01 |  | Pending | 2019-11-04 | 2019-11-08
11 | CWA | 95 | East Lake Drive SE | SGC04A | 5 | Sewer | Granite/TJ | 2019-11-01 |  | Pending | 2019-11-04 | 2019-11-08
12 | CWA | 97 | Dahlgren Street SE | SGC02B | 5 | Sewer | Granite/TJ | 2019-10-17 | 2019-10-22 | Pending | 2019-11-04 | 2019-11-08
13 | CWA | 2352 | Oakview Road NE | SGC03 | 5 | Sewer | Granite/TJ | 2019-10-31 | 2019-11-01 | Pending | 2019-11-04 | 2019-11-12
14 | CWA | 2529 | Hosea L Williams Drive SE | SGC04A | 5 | Sewer | Granite/TJ |  |  | Pending | 2019-11-05 | 2019-11-05
15 | CWA | 2803-2839 | East Pharr Road | SGC04A | 5 | Sewer | Granite/TJ |  |  | Pending | 2019-11-05 | 2019-11-11
16 | CWA | 67 | Willow Wood Circle SE | SGC04A | 5 | Sewer | Granite/TJ |  |  | Pending | 2019-11-05 | 2019-11-11
17 | CWA | 54 | Rocky Ford NE | SGC03 | 5 | Sewer | Granite/TJ |  |  | Pending | 2019-11-06 | 2019-11-06
18 | CWA | 851 | Paoli Avenue SE | SGC01A | 5 | Sewer | Granite/TJ |  |  | Pending | 2019-11-06 | 2019-11-12
19 | CWA | 64 | Daniel Avenue NE | CGC04A | 5 | Sewer | Granite/TJ |  |  | Pending | 2019-11-06 | 2019-11-12
20 | CWA | 34 | East Lake Drive NE | SGC03 | 5 | Sewer | Granite/TJ |  |  | Pending | 2019-11-07 | 2019-11-07
21 | CWA | 2007 | Bixby Street SE | SGC01C | 5 | Sewer | Granite/TJ |  |  | Pending | 2019-11-07 | 2019-11-13
22 | CWA | 1694 | Van Epps Street SE | SGC01B | 5 | Sewer | Granite/TJ |  |  | Pending | 2019-11-08 | 2019-11-14
23 | CWA | 1969 | Flat Shoals Road | SGC01A | 5 | Sewer | Granite/TJ |  |  | Pending | 2019-11-09 | 2019-11-09
24 | CWA | 1642 | Van Epps Street SE | SGC01B | 5 | Sewer | Granite/TJ |  |  | Pending | 2019-11-12 | 2019-11-18
25 | CWA | 2761 | Arbor Avenue SE | SGC04A | 5 | Sewer | Granite/TJ |  |  | Pending | 2019-11-12 | 2019-11-18
26 | CWA | 76 | Spence Avenue SE | SGC04A | 5 | Sewer | Granite/TJ |  |  | Pending | 2019-11-12 | 2019-11-18
27 | CWA | 2352 | Oakview Road NE | SGC03 | 5 | Sewer | Granite/TJ |  |  | Pending | 2019-11-14 | 2019-11-22
28 | CWA | 2313 | Hosea L Williams Drive NE | SGC03 | 5 | Sewer | Granite/TJ |  |  | Pending | 2019-11-18 | 2019-11-22
29 | CWA | 2003 | Ridgedale Road NE | SGC04A | 5 | Sewer | Granite/TJ |  |  | Pending | 2019-11-18 | 2019-11-22