## Contractor Schedule
Day | Planned Traffic Interruptions & Water Shut Offs Associated with Major Projects
| Crew 1 | Crew 2 | Crew 3 | Crew 4 | Crew 5
Sun | No Work | No Work | No Work | No Work | No Work
Mon | Various locations | Wieuca Rd NE | Hemphill Steam Pump Station | 189 Decatur St. SE. | Nelson St SW
| Activity: Milling/Paving | Activity: Tie-in | Activity: Discharge Header pipe replacement | Activity: FH replacement | Activity: restoration
| # of Customers Affected: 0 | # of Customers Affected: 7 | # of Customers Affected: 0 | # of Customers Affected: 0 | # of Customers Affected: 5 businesses, 2 apartment complex
| Working Hours: 9am-4pm | Working Hours: 9am-4pm | Working Hours: 7am-5pm | Working Hours: 9am-4pm | Working Hours: 9am-4pm
| Water interruption: No | Water interruption: No | Water interruption: No | Water interruption: No | Water interruption: Yes
| Impact Zone: N/A | Impact Zone: from GA 400 to Phipps Blvd | Impact Zone: N/A | Impact Zone: N/A | Impact Zone: from Haynes St. to Mangum St.
| Traffic Impacts: TBD | Traffic Impacts: Northbound lane on Wieuca Rd NE | Traffic Impacts: N/A | Traffic Impacts: N/A | Traffic Impacts: Southbound lane on Nelson St. SW
Tue | Various locations | Wieuca Rd NE | Hemphill Steam Pump Station | 3319 Rabun Dr. SW. | William Holmes Border Sr. Dr and Edgewood
| Activity: Milling/Paving | Activity: Tie-in | Activity: Discharge Header pipe replacement | Activity: FH replacement | Activity: potholing
| # of Customers Affected: 0 | # of Customers Affected: 7 | # of Customers Affected: 0 | # of Customers Affected: 30 | # of Customers Affected: 0
| Working Hours: 9am-4pm | Working Hours: 9am-4pm | Working Hours: 7am-5pm | Working Hours: 9am-4pm | Working Hours: 9am-4pm
| Water interruption: No | Water interruption: No | Water interruption: No | Water interruption: Yes | Water interruption: Yes
| Impact Zone: N/A | Impact Zone: from GA 400 to Phipps Blvd | Impact Zone: N/A | Impact Zone: Raburn Street from Browniee Rd SW to Hiawassee Dr SW | Impact Zone: from Haynes St. to Mangum St.
| Traffic Impacts: TBD | Traffic Impacts: Northbound lane on Wieuca Rd NE | Traffic Impacts: N/A | Traffic Impacts: N/A | Traffic Impacts: Southbound lane on Nelson St. SW
Wed | Various locations | Wieuca Rd NE | Hemphill Steam Pump Station | 1787 Brewer BLVD SW | William Holmes Border Sr. Dr and Edgewood
| Activity: Milling/Paving | Activity: Restoration | Activity: Discharge Header pipe replacement | Activity: FH replacement | Activity: Tie-in
| # of Customers Affected: 0 | # of Customers Affected: 0 | # of Customers Affected: 0 | # of Customers Affected: 25 | # of Customers Affected: 0
| Working Hours: 9am-4pm | Working Hours: 9am-4pm | Working Hours: 7am-5pm | Working Hours: 9am-4pm | Working Hours: 9am-4pm
| Water interruption: No | Water interruption: No | Water interruption: No | Water interruption: Yes | Water interruption: Yes
| Impact Zone: N/A | Impact Zone: from GA 400 to Phipps Blvd | Impact Zone: N/A | Impact Zone: Lisbon Dr between Brewer Boulevard SW and Bridgewater St SW | Impact Zone: from Haynes St. to Mangum St.
| Traffic Impacts: TBD | Traffic Impacts: Northbound lane on Wieuca Rd NE | Traffic Impacts: N/A | Traffic Impacts: N/A | Traffic Impacts: Southbound lane on Nelson St. SW
Thu | Various locations | Wieuca Rd NE | Hemphill Steam Pump Station | 3039 1st Ave SW | William Holmes Border Sr. Dr and Edgewood
| Activity: Milling/Paving | Activity: Restoration | Activity: Discharge Header pipe replacement | Activity: FH replacement | Activity: restoration
| # of Customers Affected: 0 | # of Customers Affected: 0 | # of Customers Affected: 0 | # of Customers Affected: 20 | # of Customers Affected: 0
| Working Hours: 9am-4pm | Working Hours: 9am-4pm | Working Hours: 7am-5pm | Working Hours: 9am-4pm | Working Hours: 9am-4pm
| Water interruption: No | Water interruption: No | Water interruption: No | Water interruption: No | Water interruption: Yes
| Impact Zone: N/A | Impact Zone: from GA 400 to Phipps Blvd | Impact Zone: N/A | Impact Zone: From N/A | Impact Zone: from Haynes St. to Mangum St.
| Traffic Impacts: TBD | Traffic Impacts: Northbound lane on Wieuca Rd NE | Traffic Impacts: N/A | Traffic Impacts: 1st Avenue SW between Mt Zion Rd SW and 5th ST SW | Traffic Impacts: Southbound lane on Nelson St. SW
Fri | Various locations | Wieuca Rd NE | Hemphill Steam Pump Station | 1994 Bent Creek Way SW | William Holmes Border Sr. Dr and Edgewood
| Activity: Milling/Paving | Activity: Restoration | Activity: Discharge Header pipe replacement | Activity: FH replacement | Activity: restoration
| # of Customers Affected: 0 | # of Customers Affected: 0 | # of Customers Affected: 0 | # of Customers Affected: 0 | # of Customers Affected: 0
| Working Hours: 9am-4pm | Working Hours: 9am-4pm | Working Hours: 7am-5pm | Working Hours: 9am-4pm | Working Hours: 9am-4pm
| Water interruption: No | Water interruption: No | Water interruption: No | Water interruption: No | Water interruption: Yes
| Impact Zone: N/A | Impact Zone: from GA 400 to Phipps Blvd | Impact Zone: N/A | Impact Zone: From N/A | Impact Zone: from Haynes St. to Mangum St.
| Traffic Impacts: TBD | Traffic Impacts: Northbound lane on Wieuca Rd NE | Traffic Impacts: N/A | Traffic Impacts: N/A | Traffic Impacts: Southbound lane on Nelson St. SW
Sat | No Work | No Work | No Work | No Work | No Work